| Month | INFORMATION (DATA) | PLANNING (SYSTEMS) | IMPLEMENTATION (PRACTICES) | COMMUNICATION WITH STAFF, FAMILIES and Community |
| --- | --- | --- | --- | --- |
| Before Students Return | - Review prior year’s ODR graphs, suspension, ethnicity, attendance, & academic data | - Establish monthly Universal Team meetings - Establish schedule for reporting to & celebrating with staff (plan at least 3 times per year) - Establish schedule for teaching Cool Tools/Behavior lessons- - Establish schedule for completing Evaluation Tools - Plan for staff, student, family, and bus driver kick-offs - Plan for how Universal Team will provide data/coordinate with team/staff managing secondary/ tier 2 & tertiary/ tier 3 interventions | - Conduct staff kick off | - Disseminate information on school-wide behavior support program to staff, families and community members Provide home matrices Send letter to local media/coordinate with District PR representative |
| 1st Week of School |  | - Familiarize yourself with pbsapps.org website for completing Team Implementation Checklist (TIC), PBIS Self- Assessment Survey (SAS), and the Safety Survey (SSS). Contact network office with questions-evalteam@pbisillinois.org - Take pictures for stakeholder communication | - Conduct student and family kick-offs - Distribute Staff/Students kick-off surveys - Conduct bus driver kick-off | - Send kick off stories to media |
| September | - Review ODR graphs, suspension, ethnicity, attendance, & academic data - Review results of kick-off evaluation surveys | - Convene Universal Team meeting(s)-identify team roles and responsibilities - Develop needed Cool Tool/Behavior lessons based on current data - Develop Teaching Schedule - Complete PBIS SAS (online at pbsapps.org) if completed in fall previous school year - Complete PBIS School Safety Survey (on pbsapps.org) if completed in fall previous school year) - Familiarize yourself with the Benchmarks of Quality (BoQ), which can be downloaded from www.pbisillinois.org under Evaluation Tools. Contact network office with questions- evalteam@pbisillinois.org - Take pictures for stakeholder communication | - Schedule time for staff to complete SAS online - Conduct celebrations, if applicable (include families) | - Review results of kick-off evaluation survey - Family/Community Newsletters - Send success stories to media |
| October | - Review ODR graphs, suspension, ethnicity, attendance, academic data - Review results of PBIS SAS for action planning | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lessons - Plan for fall booster - Complete TIC (if new team or earned less than 70% on previous BoQ) - Analyze school-wide data to determine needed school-wide/grade-wide interventions - Take pictures for stakeholder communication | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Reward all staff (include bus drivers and other support staff) - Review results of TIC for action planning - Determine progress monitoring data related to intervention/action plan | - Review PBIS SAS/SSS results - Utilize school-wide data to determine which behaviors/procedures need to be taught/retaught or acknowledged at higher rate (consider this information for a teaching learning example) - Family/Community Newsletters - Send success stories to media |
| November | - Review ODR graphs, suspension, ethnicity, attendance, & academic data | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lesson(s) - Plan for fall school board presentation - Review Action Plan - Complete PoI with External Coach by mid November - Take pictures for stakeholder communication | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Conduct fall booster - Check with new students, staff and families to see if they understand expectations & reward system (checklist/survey) - Analyze progress monitoring data to determine intervention effectiveness (revise plan as needed) | - Present school-wide data update AND decide which behaviors/procedures need to be taught/retaught or acknowledged at higher rate - Family/Community Newsletters - Send success stories to media |
| December | - Review ODR graphs, suspension, ethnicity, attendance, & academic data - Review Education Environment (EE) data from your school - Review results of PoI for action planning | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lesson(s) - Review Action Plan - Plan booster/motivator to keep staff using PBIS - Plan for re-teaching of expectations first day back from break -Take pictures for stakeholder communication | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Present to school board-use pictures - Reward all staff (include bus drivers and other support staff) - Continue to progress monitor data to determine intervention effectiveness – | - Continue to keep stakeholders informed on results of intervention data - Send success stories to media |
| January | - Review ODR graphs, suspension, ethnicity, attendance, & academic data | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lesson(s) schedule time to teach - Complete TIC - Plan reinforcement for indoor recess days - Take pictures for stakeholder communication | - Re-teach school-wide expectations first day back from break - Conduct celebrations, if applicable (include applicable) - Reward staff - Review results of TIC and revise action plan, as needed - Continue to progress monitor data to determine intervention effectiveness | - Continue to keep stakeholders informed on results of intervention data - Family/Community Newsletters - Send success stories to media |
| February | - Review ODR graphs, suspension, ethnicity, attendance, & academic data. | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lesson(s) - Plan for spring booster - Discuss the BoQ process as a team - Take pictures for stakeholder communication | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Continue to progress monitor data to determine intervention effectiveness | - Continue to keep stakeholders informed on results of intervention data - Family/Community Newsletters - Send success stories to media |
| March | - Review ODR graphs, suspension, ethnicity,, attendance, & academic data | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lesson(s) - Complete TIC - Schedule time for staff to complete SAS online at pbsapps.org. Contact network office with questions-evalteam@pbisillinois.org - Complete BoQ with team members (to be completed by mid April) - Take pictures for stakeholder communication | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Review results of TIC and revise action plan, as needed. - Conduct spring booster - Reward staff - Review results of SSS with team - Continue to progress monitor data to determine intervention effectiveness | - Continue to keep stakeholders informed on results of intervention data - Family/Community Newsletters - Send success stories to media |
| April | - Review ODR graphs, suspension, ethnicity,, attendance, & academic data | - Convene Universal Team meeting(s) - Develop needed Cool Tool/Behavior lesson(s) - Plan for the end-of-the-year school board presentation - Plan for team membership changes for next year (include family members) - Review Action Plan and begin to set goals for next year - Plan for end-of-year celebration - Complete Spring PoI (to be completed by mid April) -Complete SSS survey. Contact Network Office with questions—eval team@pbisillinois.org - Complete recognition packet application (to submit by mid May) -Take pictures for stakeholder communication | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Complete action plan based on BoQ/PoI/SAS results - Continue to progress monitor data to determine intervention effectiveness | - Continue to keep stakeholders informed on results of intervention data - Family/Community Newsletters - Send success stories to media |
| May /June | - Review ODR graphs, suspension, ethnicity, attendance, & academic data summaries for year | - Convene Universal Team meeting(s) - Schedule summer team work time, if applicable - Send completed recognition packet to office by mid May | - Teach scheduled Cool Tool/Behavior lesson(s) - Conduct celebrations, if applicable (include families) - Present to school board- use pictures - Reward staff - Continue to progress monitor data to determine intervention effectiveness | - Continue to keep stakeholders informed on results of intervention data - Family/Community Newsletters - Send success stories to media |

|  | Team Meeting Dates |  | Fall Kick-Off |  | Report SAS Survey Results |  | Team Checklist and/or TFI Completed |  | Faculty Updates: Activities/ Data |  | Boosters |  | School Climate Survey Completed |  | Celebrations/ Intermittent Acknowledge |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AUGUST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SEPTEMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OCTOBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NOVEMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DECEMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| JANUARY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FEBRUARY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MARCH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| APRIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MAY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| JUNE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| JULY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Cool Tool Teaching Plan: